## High Level
ID | Feature/Goal | Owner | Status | ETA |  |  | Effort (in man hours) |  |  | Comments
|  |  |  | Estimate | Forecast | Actual | Estimate | Forecast | Actual
RD0001 | Learn SDN and OpenFlow Basics | All | Completed | 2012-09-06 | 2012-09-06 | 2012-09-06 | 8 | 8 | 8 |  | In Progress
RD0002 | Learn OpenFlow in detail | All | Completed | 2012-09-14 | 2012-09-14 | 2012-09-14 | 40 | 40 | 40 |  | Delayed
RD0003 | Complete OpenFlow tutorial shared by Bill | All | Completed | 2012-09-21 | 2012-09-21 | 2012-09-21 | 40 | 40 | 40 |  | Completed
RD0004 | Study and experiment with POX controller | Anil | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 40 | 40 | 40 |  | Yet to start
RD0005 | Study and experiment with Beacon controller | Raghav | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 40 | 40 | 40 |  | Postponed
RD0006 | Study and experiment with FloodLight controller | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 24 | 24 | 24
RD0007 | Study and experiment with OFTest framework | Anil | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 24 | 24 | 24
DOC0001 | Prepare documents/PPTs | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 8 | 8 | 8
POC0001 | PoC showing interaction between various components of OpenFlow | Anil, Raghav | Completed | 2012-10-22 | 2012-10-22 | 2012-10-22 | 128 | 128 | 128
DES0001 | SRS for SDN Automation framework | Sriram, Sandeep | Completed | 2012-10-15 | 2012-10-19 | 2012-10-19 | 40 | 40 | 40
DES0002 | HLD for SDN Automation framework | Sriram, Sandeep | Completed | 2012-11-09 | 2012-11-09 | 2012-11-09 | 40 | 40 | 40
FEAT0001 | Parameterisation | Anil, Raghav | Completed | 2012-11-16 | 2012-11-16 | 2012-11-16 | 104 | 104 | 104 | Deadline is more in this case because the engineers will be off.
TEST0001 | FlowVisor testing | Anil | Completed | 2012-12-10 | 2012-12-10 | 2012-12-10 | 92 | 92 | 92
FEAT0002 | Core Connectivity | Raghav | Completed | 2012-12-12 | 2012-12-12 | 2012-12-12 | 80 | 80 | 80
FEAT0003 | Logging | Anil | Completed | 2012-11-23 | 2012-11-23 | 2012-11-29 | 50 | 50 | 104
FEAT0004 | OpenSpeak authoring | Raghav | Completed | 2013-01-08 | 2013-01-08 | 2013-01-08 | 152 | 152 | 152
FEAT0005 | Test handling | Anil | Completed | 2013-01-08 | 2013-01-08 | 2013-01-08 | 160 | 160 | 160
AUTO0001 | FlowVisor test automation | Anil, Raghav | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 184 | 184 | 184
DES0001 | UI Mock-ups and design docs for phase II | Sriram, Sandeep | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 80 | 80 | 80 | Design work for phase II will start in parallel with last leg of phase I to avoid delays. Breakdown of this task will be provided later.
CLEANUP0001 | Fix the issues and clean-up the code. | Anil | Completed | 2013-01-28 | 2013-01-28 | 2013-01-28 | 64 | 64 | 64
TEST0002 | OFA testing and Automation | Anil, Raghav | In Progress | 2013-02-08 | 2013-02-08 |  | 144 | 144
DES0002 | SRS draft for Phase II. | Sriram | In Progress | 2013-02-04 | 2013-02-04 |  | 40 | 40

## Task Details
Feature/Goal | ID | Task | Owner | Status | ETA |  |  | Effort |  |  | Comments | References
[5 empty] | Estimate | Forecast | Actual | Estimate | Forecast | Actual
RD0001 | TASK0001 | Software Defined Network introduction. | All | Completed | 2012-09-06 | 2012-09-06 | 2012-09-06 | 4 | 4 | 4 |  | http://en.wikipedia.org/wiki/Software_Defined_Networking | In Progress
| TASK0002 | Open Flow introduction | All | Completed | 2012-09-06 | 2012-09-06 | 2012-09-06 | 4 | 4 | 4 |  | http://en.wikipedia.org/wiki/Software_Defined_Networking | Delayed
Completed
RD0002 | TASK0001 | Learn OpenFlow. | All | Completed | 2012-09-10 | 2012-09-10 | 2012-09-10 | 12 | 12 | 12 |  | http://www.openflow.org/wp/learnmore/ | Yet to start
| TASK0002 | Understand the OpenFlow Specification | All | Completed | 2012-09-10 | 2012-09-10 | 2012-09-10 | 6 | 6 | 6 |  | http://www.openflow.org/documents/openflow-spec-v1.1.0.pdf | Postponed
| TASK0003 | Get the information from videos. | All | Completed | 2012-09-12 | 2012-09-12 | 2012-09-12 | 10 | 10 | 10 |  | www.openflow.org/videos/
| TASK0004 | Learn more about OpenFlow | All | Completed | 2012-09-14 | 2012-09-14 | 2012-09-14 | 12 | 12 | 12 |  | http://demo.ipspace.net/get/OpenFlow
RD0003 | TASK0001 | Open Flow introduction and Openflow protocol. | All | Completed | 2012-09-17 | 2012-09-17 | 2012-09-17 | 6 | 6 | 6 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial
| TASK0002 | Understand the OpenFlow Specification | All | Completed | 2012-09-18 | 2012-09-18 | 2012-09-18 | 10 | 10 | 10 |  | http://www.openflow.org/documents/openflow-spec-v1.1.0.pdf
| TASK0003 | Introduction to build a network using mininet. | All | Completed | 2012-09-19 | 2012-09-19 | 2012-09-19 | 3 | 3 | 3 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial
| TASK0004 | Perform the ping test for the same network | All | Completed | 2012-09-19 | 2012-09-19 | 2012-09-19 | 3 | 3 | 3 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial
| TASK0005 | Capturing the Open-Flow Protocol packets using Wireshark, tcpdump and study about the messages . | All | Completed | 2012-09-20 | 2012-09-20 | 2012-09-20 | 10 | 10 | 10 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial
| TASK0006 | Study about adding flow entry into flow table of switch. | All | Completed | 2012-09-21 | 2012-09-21 | 2012-09-21 | 8 | 8 | 8 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial
RD0004 | TASK0001 | Verify Hub Behaviour with tcpdump | Anil | Completed | 2012-09-24 | 2012-09-24 | 2012-09-24 | 6 | 6 | 5 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_A:_POX_.28Python.29
| TASK0002 | Work with of_tutorial component to check the switch behaviour | Anil | Completed | 2012-09-25 | 2012-09-25 | 2012-09-25 | 6 | 6 | 7 |  | https://github.com/noxrepo/pox
| TASK0003 | Send OpenFlow messages with POX | Anil | Completed | 2012-09-26 | 2012-09-26 | 2012-09-26 | 8 | 8 | 6 |  | http://www.noxrepo.org/pox/about-pox/
| TASK0004 | Parse Packets with the POX packet libraries | Anil | Completed | 2012-09-27 | 2012-09-27 | 2012-09-27 | 8 | 8 | 10 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_A:_POX_.28Python.29
| TASK0005 | Work on the create component to behave like switch and hub with specified Rules and Actions | Anil | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 12 | 12 | 12 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_A:_POX_.28Python.29
RD0005 | TASK0001 | Practice with the Beacon Controller , by creating the Learn and forward switch. | Raghav | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 16 | 16 | 16 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_B:_Beacon_.28Java.29 https://openflow.stanford.edu/forums/forum/4-beacon-general/
| TASK0002 | Practice with creating a new bundle for Beacon controller which will interact with Beacon core bundle. | Raghav | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 8 | 8 | 8 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_B:_Beacon_.28Java.29 https://openflow.stanford.edu/forums/forum/4-beacon-general/
| TASK0003 | To create a learning switch and do the ping test | Raghav | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 8 | 8 | 8 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_B:_Beacon_.28Java.29 https://openflow.stanford.edu/forums/forum/4-beacon-general/
| TASK0004 | To create a learning switch and forward switch and perform a test | Raghav | Completed | 2012-09-28 | 2012-09-28 | 2012-09-28 | 8 | 8 | 8 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_B:_Beacon_.28Java.29 https://openflow.stanford.edu/forums/forum/4-beacon-general/
RD0006 | TASK0001 | To install FloodLight Controller and also setup VM for the same. | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-09-28 | 8 | 8 | 8 |  | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Controller_Choice_B:_Beacon_.28Java.29 https://openflow.stanford.edu/forums/forum/4-beacon-general/
| TASK0002 | Setup VM for the FloodLight Controller for using Quantum. | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-10-01 | 8 | 8 | 8 |  | http://floodlight.openflowhub.org/getting-started/ http://floodlight.openflowhub.org/developing-floodlight/
| TASK0003 | To create learn and forward open-flow switch using FloodLight Controller | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-10-02 | 8 | 8 | 8 |  | http://floodlight.openflowhub.org/getting-started/ http://floodlight.openflowhub.org/developing-floodlight/
| TASK0004 | To create learn and forward open-flow switch using FloodLight Controller | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 4 | 4 | 4 |  | http://floodlight.openflowhub.org/getting-started/ http://floodlight.openflowhub.org/developing-floodlight/
| TASK0004 | Using FloodLight, to create a bundle that will watch for new MAC addresses that have not been seen before, and log the MAC and switch they were seen on. | Raghav | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 4 | 4 | 4 |  | http://floodlight.openflowhub.org/getting-started/ http://floodlight.openflowhub.org/developing-floodlight/
RD0007 | TASK0001 | Architectural Overview, Basics of unittest | Anil | Completed | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2 | 2 | 2 |  | http://www.openflow.org/wk/index.php/OFTestTutorial
| TASK0002 | Key Class Hierarchies and Components | Anil | Completed | 2012-10-01 | 2012-10-01 | 2012-10-01 | 6 | 6 | 6 |  | http://www.openflow.org/wk/index.php/OFTestTutorial
| TASK0003 | Work with basic Examples | Anil | Completed | 2012-10-02 | 2012-10-02 | 2012-10-02 | 6 | 6 | 6 |  | http://www.openflow.org/wk/index.php/OFTestTutorial
| TASK0004 | Practice Test Utilities | Anil | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 5 | 5 | 5 |  | http://www.openflow.org/wk/index.php/OFTestTutorial
| TASK0005 | Practice Passing Parameters to Tests and Other Test Conventions | Anil | Completed | 2012-10-03 | 2012-10-03 | 2012-10-03 | 5 | 5 | 5 |  | http://www.openflow.org/wk/index.php/OFTestTutorial
DOC0001 | TASK0001 | Prepare a introduction presentation. | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 2 | 2 | 2 |  | All previous available links and documents
| TASK0002 | To prepare document prepared about read so far. | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 2 | 2 | 2 |  | All previous available links and documents
| TASK0003 | Create mind map for the OpenFlow. | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 1 | 1 | 1 |  | All previous available links and documents
| TASK0004 | Mind map creation for Beacon Controller. | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 1 | 1 | 1 |  | All previous available links and documents
| TASK0005 | Mind map creation for NOX | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 1 | 1 | 1 |  | All previous available links and documents
| TASK0006 | To Create Mind Map for Flood Light Controller | All | Completed | 2012-10-04 | 2012-10-04 | 2012-10-04 | 1 | 1 | 1 |  | All previous available links and documents
POC0001 | TASK0001 | Config file parser | Raghav | Completed | 2012-10-08 | 2012-10-08 | 2012-10-09 | 8 | 8 | 9
| TASK0002 | Logger class | Raghav | Completed | 2012-10-08 | 2012-10-08 | 2012-10-08 | 8 | 8 | 7
| TASK0003 | Core test engine | Anil, Raghav | Completed | 2012-10-12 | 2012-10-12 | 2012-10-12 | 32 | 32 | 30
| TASK0004 | Basic driver component | Anil | Completed | 2012-10-16 | 2012-10-16 | 2012-10-16 | 16 | 16 | 16
| TASK0005 | Switch driver | Anil, Raghav | Completed | 2012-10-17 | 2012-10-17 | 2012-10-17 | 8 | 8 | 8 | As according to POC it has been completed and its enhancement will continue them later as part of the framework.
| TASK0006 | Host driver | Anil, Raghav | Completed | 2012-10-18 | 2012-10-18 | 2012-10-18 | 8 | 8 | 8 | As according to POC it has been completed and its enhancement will continue them later as part of the framework.
| TASK0007 | Controller driver (for POX) | Raghav | Completed | 2012-10-18 | 2012-10-18 | 2012-10-18 | 32 | 32 | 32
| TASK0008 | Sample test and integration | Anil | Completed | 2012-10-22 | 2012-10-22 | 2012-10-22 | 16 | 16 | 16
| TASK0009 | Argument parser | Raghav | Completed | 2012-10-22 | 2012-10-22 | 2012-10-22 | 6 | 6
| TASK0010 | Prepare pydoc for all available classes | Raghav | Completed | 2012-10-23 | 2012-10-23 | 2012-10-23 | 4 | 4 | 4
| TASK0011 | Separate Topology File and Params File and create their parsers | Anil | Completed | 2012-10-23 | 2012-10-23 | 2012-10-23 | 6 | 6 | 6
| TASK0012 | To Add device level logs into hierarchy | Anil | Completed | 2012-10-23 | 2012-10-23 | 2012-10-23 | 2 | 2 | 2
| TASK0013 | Add Topology part into the header output of console, report and log files and also to provide proper formatting | Raghav | Completed | 2012-10-23 | 2012-10-23 | 2012-10-23 | 6 | 6 | 6
| TASK0014 | Add two new log levels EXACT and REPORT for logging | Raghav | Completed | 2012-10-25 | 2012-10-25 | 2012-10-25 | 8 | 8 | 8
| TASK0015 | To prepare execution Demo video of created POC so far | Anil | Completed | 2012-10-26 | 2012-10-26 | 2012-10-26 | 5 | 5 | 5
| TASK0016 | Prepare mail sending Feature for the test Run | Anil | Completed | 2012-10-26 | 2012-10-26 | 2012-10-26 | 3 | 3 | 3 | As according to POC it has been completed and its enhancement will continue them later as part of the framework
| TASK0017 | To prepare assert in order to get the test case result | Anil | Completed | 2012-10-26 | 2012-10-26 | 2012-10-26 | 2 | 2 | 2
| TASK0018 | To Add captions in execution Demo video of created POC so far | Anil, Raghav | Completed | 2012-10-26 | 2012-10-26 | 2012-10-26 | 3 | 3 | 3
| TASK0019 | Add feature to get Test Summary and each test summary into console , report and log files | Raghav | Completed | 2012-10-26 | 2012-10-26 | 2012-10-26 | 5 | 5 | 5
DES0001 | TASK0001 | Prepare draft SRS | Sriram | Completed | 2012-10-18 | 2012-10-18 | 2012-10-22 | 32 | 32 | 32 | Delayed as the scope of SRS was bigger than planned. Had to prepare OpenSpeak sepc document as well.
| TASK0002 | Review and freeze final SRS | Sriram/Renil/Rama/Venkat | Completed | 2012-10-19 | 2012-10-19 | 2012-10-19 | 8 | 8 | 8
DES0002 | TASK0001 | Research and identify CLI framework | Sriram/Sandeep | Completed | 2012-11-02 | 2012-11-02 | 2012-11-02 | 8 | 8 | 8 | Slected the cmd module of the python.
| TASK0002 | Design class templates | Sandeep | Completed | 2012-11-06 | 2012-11-06 | 2012-11-06 | 8 | 8 | 8
| TASK0003 | Specify styling guidelines | Sandeep | Completed | 2012-11-09 | 2012-11-09 | 2012-11-09 | 8 | 8 | 8
FEAT0001 | TASK0001 | Complete assertion handling | Raghav | Completed | 2012-11-02 | 2012-11-02 | 2012-11-02 | 8 | 8 | 8
| TASK0002 | Step wise test execution | Anil | Completed | 2012-11-02 | 2012-11-02 | 2012-11-02 | 8 | 8 | 6
| TASK0003 | Case and step level parameterisation | Anil | Completed | 2012-11-06 | 2012-11-06 | 2012-11-06 | 16 | 16 | 16 | Deadline is more in this case because the engineers will be off.
| TASK0004 | Device level parameterisation in topology file | Anil | Completed | 2012-11-06 | 2012-11-06 | 2012-11-06 | 8 | 8 | 8 | Deadline is more in this case because the engineers will be off.
| TASK0005 | Testing, documentation and examples | Anil | Completed | 2012-11-16 | 2012-11-16 | 2012-11-16 | 8 | 8 | 8
TEST0001 | TASK0001 | Setup FlowVisor environment and verify | Anil | Completed | 2012-11-09 | 2012-11-09 | 2012-11-08 | 16 | 16 | 16 |  | https://openflow.stanford.edu/display/ONL/FlowVisor
| TASK0002 | Execute basic flows described in Masa's document | Anil | Completed | 2012-11-20 | 2012-11-20 | 2012-11-20 | 48 | 48 | 48 | Deadline is more in this case because the engineers will be off. | http://www.openflow.org/wk/index.php/OpenFlow_Tutorial#Control_a_Slice_of_a_real_Network https://openflow.stanford.edu/display/ONL/Flowvisor
| TASK0003 | Troubleshoot with Masa's help if needed | Anil | Completed | 2012-11-20 | 2012-11-20 | 2012-11-20 | 12 | 12 | 12
| TASK0004 | Complete basic manual test cycle | Anil | Completed | 2013-01-15 | 2013-01-15 | 2013-01-15 | 16 | 16 | 16
FEAT0002 | TASK0001 | Cleanup core drivers and organize | Raghav | Completed | 2012-11-21 | 2012-11-21 | 2012-11-21 | 8 | 8 | 8
| TASK0002 | Define driver templates for Switch, Host, Emulator and Network Slicer | Raghav | Completed | 2012-11-22 | 2012-11-22 | 2012-11-22 | 8 | 8 | 8
| TASK0003 | Write experimental mode method | Raghav | Completed | 2012-11-23 | 2012-11-23 | 2012-11-23 | 8 | 8 | 8
| TASK0004 | Implement FlowVisor driver | Anil | Completed | 2013-01-21 | 2013-01-21 |  | 16 | 16
| TASK0005 | Implement Mininet driver | Raghav | Completed | 2012-11-29 | 2012-11-29 | 2012-11-29 | 8 | 8 | 8
| TASK0006 | Implement POX driver | Raghav | Completed | 2012-11-30 | 2012-11-30 | 2012-12-03 | 16 | 16 | 24 | Loosely coupled or CLI is completed. Need to figure-out a way for API level integration with help of Masa
| TASK0007 | Testing, documentation and examples | Raghav | Completed | 2012-12-03 | 2012-12-03 | 2012-12-05 | 16 | 16 | 20
FEAT0003 | TASK0001 | Cleanup all logs and conform to SRS | Anil | Completed | 2012-11-19 | 2012-11-19 | 2012-11-19 | 8 | 8 | 8
| TASK0002 | Component level logging | Anil | Completed | 2012-11-21 | 2012-11-21 | 2012-11-27 | 18 | 18 | 28 | Delayed because of the updating of the session logs with the headers and the proper console output. And component log's handling shifted from ofautomation to the component class.
| TASK0003 | Error and exception logging | Anil | Completed | 2012-11-23 | 2012-11-23 | 2012-11-27 | 16 | 16 | 20
| TASK0004 | Testing, documentation and examples | Anil | Completed | 2012-11-23 | 2012-11-23 | 2012-11-29 | 8 | 8 | 48
FEAT0004 | TASK0001 | Define basic compiler methods and templates | Raghav | Completed | 2012-12-10 | 2012-12-11 | 2012-12-11 | 8 | 8 | 16
| TASK0002 | Translate NAME, CASE, STEP and COMMENT definitions and append header/footer sections | Raghav | Completed | 2012-12-17 | 2012-12-17 | 2012-12-14 | 32 | 32 | 24
| TASK0003 | Component interaction compiling | Raghav | Completed | 2012-12-20 | 2012-12-20 | 2012-12-20 | 24 | 24 | 24
| TASK0004 | Assertion compiling | Raghav | Completed | 2012-12-24 | 2012-12-24 | 2012-12-24 | 16 | 16 | 16
| TASK0005 | Logging compiling | Raghav | Completed | 2012-12-26 | 2012-12-26 | 2012-12-26 | 8 | 8 | 8
| TASK0006 | Programming keywords compiling | Raghav | Completed | 2013-01-02 | 2013-01-02 | 2013-01-02 | 32 | 32 | 32
| TASK0007 | Conjunction | Raghav | Completed | 2013-01-07 | 2013-01-07 | 2013-01-07 | 24 | 24 | 24
| TASK0008 | Testing, documentation and examples | Raghav | Completed | 2013-01-08 | 2013-01-08 | 2013-01-08 | 8 | 8 | 8
FEAT0005 | TASK0001 | Explore and learn selected CLI framework | Anil | Completed | 2012-12-12 | 2012-12-12 | 2012-12-12 | 16 | 16 | 16
| TASK0002 | Prepare basic CLI shell with echo and help | Anil | Completed | 2012-12-14 | 2012-12-14 | 2012-12-14 | 16 | 16 | 16
| TASK0003 | Test execution via CLI | Anil | Completed | 2012-12-18 | 2012-12-18 | 2012-12-18 | 16 | 16 | 16
| TASK0004 | Test compilation via CLI | Anil | Completed | 2012-12-20 | 2012-12-20 | 2012-12-20 | 16 | 16 | 16
| TASK0005 | Pause and resume | Anil | Completed | 2012-12-28 | 2012-12-28 | 2012-12-28 | 72 | 72 | 40
| TASK0006 | CLI debugger | Anil | Completed | 2013-01-03 | 2013-01-03 | 2013-01-02 | 32 | 32 | 28
| TASK0007 | Testing, documentation and examples | Anil | Completed | 2013-01-08 | 2013-01-08 | 2013-01-08 | 24 | 24 | 24
AUTO0001 | TASK0001 | Implement API driver for POX | Raghav | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 72 | 72 | 72
| TASK0002 | Implement driver for FlowVisor | Anil | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 72 | 72 | 72
| TASK0003 | Automate basic testcases for FlowVisor using FlowVisor document | Anil, Raghav | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 64 | 64 | 64
| TASK0004 | Implement the hybrid method to create the driver for any framework( Python based). | Raghav | Completed | 2013-01-28 | 2013-01-28 | 2013-01-28 | 40 | 40 | 40
CLEANUP0001 | TASK0001 | Create separate session files for all the components. | Anil | Completed | 2013-01-18 | 2013-01-18 | 2013-01-18 | 16 | 16 | 16
| TASK0002 | Organise all drivers and place under CLI/API in proper order with naming convention as fvtapidriver, poxclidriver, etc. | Anil | Completed | 2013-01-21 | 2013-01-21 | 2013-01-21 | 8 | 8 | 8
| TASK0003 | Verify CLI based drivers having the complete coverage of all the functions. And work for update all. | Anil | Completed | 2013-01-24 | 2013-01-24 | 2013-01-24 | 24 | 24 | 24
| TASK0004 | Update coverage matrix, for every driver. Prepare an XLS that shows what are all the functions available in the tool and integrated in OFA. | Anil | Completed | 2013-01-28 | 2013-01-28 | 2013-01-28 | 16 | 16 | 16
TEST0002 | TASK0001 | Prepare a test plan. | Anil, Raghav | In Progress | 2013-01-30 | 2013-01-30 |  | 32 | 32
| TASK0002 | Prepare tests and Automate by using OFA. | Raghav,Anil | Yet to start | 2013-02-08 | 2013-02-08 |  | 80 | 80
| TASK0003 | Fix Bugs and release OFA 1.0.1 | Anil, Raghav | Yet to start | 2013-02-08 | 2013-02-08 |  | 32 | 32
DES0002 | TASK0001 | SRS draft for Phase II. | Sriram | In Progress | 2013-02-04 | 2013-02-04 |  | 16 | 16